## Instructions
Downloaded From
Track Excel Project Tasks
Related tutorials
Data Validation Drop Down Lists
Create a Pivot Table
Notes
1 | Enter tasks on the ProjectTasks sheet
2 | On Summary sheet, refresh pivot table, after making changes to ProjectTasks
Get weekly Excel tips, tutorials, videos, and news
Contextures Excel Newsletter

## Summary
Sales Workbook Update Project
www.contextures.com
NOTE: Refresh the pivot tables after updating the Project Task list
Time Per Employee |  |  | Time Per File
(minutes) |  |  | (minutes)
Task For | Est Time | Act Time | File | Est Time | Act Time
Al | 90 |  | SalesData | 115 | 30
Cal | 50 |  | SalesRpts | 50
Dee | 10 |  | Grand Total | 165 | 30
Fran | 15 | 30
Grand Total | 165 | 30

## ProjectTasks
| Total Hrs Est | 2.75 |  | Sales Workbook Update Project |  | Total Hrs Actual | 0.5 |  | www.contextures.com
ID | File | Sheet | Task Type | Task Desc | Time Est Minutes | Task For | Date Done | Time Act Minutes | Notes / Questions | Q To | Replies
1 | SalesData | Sales Data | Macros | Add import button and code | 90 | Al
2 | SalesData | Lists | Change | Get new employee list | 15 | Fran | 2020-10-02 | 30 | Who has the new list? | Dee | Call Amy in HR
3 | SalesData | Settings | Change | Add named cell for export path | 10 | Dee
4 | SalesRpts | Menu | Add | Add new Menu sheet with links | 30 | Cal
5 | SalesRpts | Report | Error | Fix formula error in column J | 20 | Cal

## Lists
File | Sheet | TaskType | Names
SalesData | Intro | Add | Al
SalesRpts | Lists | Macros | Bea
| Sales Data | Change | Cal
| Settings | Error | Dee
| Menu | Format | Ed
| Report | Structure | Fran
Sales Rpt

## MyLinks
Contextures Products
Pivot Power Premium Add-in | Time-saving tools for pivot table power users
UserForms for Data Entry ebook Kit | Step by step instructions and videos
Contextures Excel Tools Add-in | Make instant backups, sort sheets, and many more tools
Data Entry Search Popup | Makes data entry easier when choosing from long list
Data Entry Popup | Select single or multiple items from a listbox, to enter in a single cell
Contextures Sites & News
Contextures Excel Newsletter | Weekly Excel tips, tutorials, videos, and news
Contextures Excel Tips Website | Hundreds of tutorials, tips and sample files
Contextures Excel Blog | Read the Excel tutorials and share your comments
Excel Pivot Tables Blog | Pivot table tutorials and tips, with comments and questions
Other Excel Products
Contextures Recommends | Other Excel tools and training, recommended by Debra